## Register
Risk register: AWS security lab (Projects 3 and 4)
Built from real lab results on 2026-10-13. Scores are my judgments (see Method). Blue cells are inputs. Ratings recalculate from the bands on the Method sheet.
ID | Asset | Risk | Evidence from the lab | Likelihood (1 to 5) | Impact (1 to 5) | Inherent score | Inherent rating | CSF 2.0 function | CSF 2.0 category | NIST 800-53 controls | Treatment | Treatment plan and reason | Control status | Owner | Target likelihood | Target impact | Target score | Target rating
R01 | AWS lab account: S3 bucket | A misconfiguration makes the bucket public and exposes its contents to anyone on the internet. | Project 3: S3 Block Public Access was on for all four settings; an attempt to attach a public read policy was refused with AccessDenied and logged by CloudTrail as PutBucketPolicy. | 3 | 5 | 15 | Critical | PROTECT | PR.DS Data Security | AC-3, AC-6, SC-7 | Reduce | Keep all four Block Public Access settings on at the account and bucket level. They sit above bucket policies and ACLs, so a bad policy cannot override them. | Implemented and tested in lab | Lab owner | 1 | 5 | 5 | Medium
R02 | IAM users: console sign in | A console user without MFA is phished or password sprayed and the attacker signs in as that user. | Project 4: the access review flagged test user ar-test-nomfa as High (console password enabled, no MFA device). | 3 | 4 | 12 | High | PROTECT | PR.AA Identity Management, Authentication and Access Control | IA-2(1), IA-2(2), AC-2 | Reduce | Require MFA with a deny policy that allows only MFA setup until MFA is present. It was proven in the policy simulator. Apply it to every console user before any real use. | Tested in simulator on a test user, not yet applied to real users | Lab owner | 1 | 4 | 4 | Low
R03 | IAM policies | A user is given broader permissions than the job needs and reads or changes data it should not touch. | Project 3: a least privilege policy passed IAM Access Analyzer with zero findings. In the policy simulator 4 of 6 test actions were implicit denies without a single deny statement. | 3 | 4 | 12 | High | PROTECT | PR.AA Identity Management, Authentication and Access Control | AC-6, AC-3 | Reduce | Write policies from the job outward, allow only listed actions and resources, and run Access Analyzer and the simulator before attaching. | Implemented and tested in lab | Lab owner | 1 | 4 | 4 | Low
R04 | IAM access keys | A long lived access key goes unused or stale, stays active, and is later leaked or reused by an attacker. | Project 4: with a simulated review date 99 days out, the review flagged ar-test-key twice (stale key over 90 days, key never used). That run used a simulated date and is labeled that way. | 3 | 4 | 12 | High | PROTECT | PR.AA Identity Management, Authentication and Access Control | IA-5, AC-2, AC-2(3) | Reduce | Run the access review on a schedule, disable keys over 90 days or never used, and prefer roles over long lived keys. | Detection built (audit_iam.py); disabling is a manual step | Lab owner | 2 | 3 | 6 | Medium
R05 | Screenshots, posts and repo | An AWS account ID, key, email or other sensitive value is published in a screenshot, video or repo file. | Projects 3 and 4: ground rule to blur the account ID, keys and email before posting; audit_iam.py never prints the account ID; key output was discarded in the runbook commands. | 3 | 4 | 12 | High | PROTECT | PR.DS Data Security | AC-22, AT-2 | Reduce | Use a pre post checklist, discard secret output in commands, and check every screenshot before it leaves the machine. | Implemented as a manual checklist | Lab owner | 1 | 4 | 4 | Low
R06 | AWS root account | The root user is taken over because it lacks MFA or has access keys. | Project 4: the baseline run reported zero findings, including the two root account checks (no MFA and root access key). This is the script's result; I did not verify root settings any other way. | 2 | 5 | 10 | High | PROTECT | PR.AA Identity Management, Authentication and Access Control | AC-6, IA-2(1), AC-2 | Reduce | Keep MFA on root, keep root access keys deleted, use root only when a task requires it, and re run the review each cycle. | Implemented; checked by audit_iam.py | Lab owner | 1 | 5 | 5 | Medium
R07 | Lab data and employer systems | Real employer, client or production data ends up in a personal lab account. | Projects 3 and 4: every dataset was test data created for the lab. The README for each project states the scope. | 2 | 5 | 10 | High | IDENTIFY | ID.AM Asset Management | RA-2, AC-22 | Avoid | Do not use real data in the lab at all. Test files and invented sample data only, and label invented data SYNTHETIC. | Implemented as a rule | Lab owner | 1 | 5 | 5 | Medium
R08 | S3 Block Public Access setting | Someone, including me, switches Block Public Access off by mistake and the change goes unnoticed. | Project 3: I switched all four settings off and back on in the lab, which showed how quick the change is in the console. | 2 | 5 | 10 | High | DETECT | DE.CM Continuous Monitoring | CM-6, SI-4 | Reduce | Add a detective control for changes to the public access block setting, such as an AWS Config rule or a CloudTrail based alarm. | Planned, not built | Lab owner | 1 | 5 | 5 | Medium
R09 | CloudTrail logs | Logging is turned off or logs are altered, so a later incident cannot be investigated. | Project 3: CloudTrail recorded the refused PutBucketPolicy attempt with the error AccessDenied, which shows logging works today. | 2 | 4 | 8 | Medium | PROTECT | PR.PS Platform Security | AU-2, AU-9 | Reduce | Keep the trail on, send logs to a separate protected bucket, and turn on log file validation. | Trail working; separate bucket and validation planned | Lab owner | 1 | 4 | 4 | Low
R10 | Security logs | Logs exist but nobody reads them, so a real attack is missed. | Project 3: CloudTrail recorded the refused PutBucketPolicy attempt, but a log only helps if someone reads it. | 3 | 3 | 9 | Medium | DETECT | DE.AE Adverse Event Analysis | AU-6, SI-4 | Reduce | Set a review cadence and an alarm for the highest value events such as root sign in, failed policy changes and IAM changes. | Planned, not built | Lab owner | 2 | 2 | 4 | Low
R11 | MFA required policy | The MFA deny policy blocks a non human user whose only credential is a long term access key, and an automated job fails. | Project 4: the simulator test with no MFA information at all returned explicitDeny, because the policy uses BoolIfExists. | 3 | 3 | 9 | Medium | PROTECT | PR.AA Identity Management, Authentication and Access Control | AC-2, CM-3 | Reduce | Attach the policy to a group for human users only and move automation to roles with temporary credentials. Test in the simulator before attaching to anyone. | Known limit documented in the Project 4 README | Lab owner | 1 | 3 | 3 | Low
R12 | Test users and policies | Test users, passwords or keys are left behind after a lab and widen the attack surface. | Project 4: cleanup commands removed both test users, their key and the lab policy, and the list commands afterward printed nothing. | 2 | 3 | 6 | Medium | IDENTIFY | ID.AM Asset Management | CM-8, AC-2 | Reduce | Write the cleanup commands before building, run them when the lab ends, and verify with list commands. | Implemented and verified for Project 4 | Lab owner | 1 | 3 | 3 | Low
R13 | Access review process | The review misses new users because IAM serves a cached credential report for up to four hours. | Project 4: my first re run after creating the test users still showed the old two users. I added a fresh mode that reads live IAM data. | 2 | 2 | 4 | Low | IDENTIFY | ID.RA Risk Assessment | CA-7, AC-2 | Reduce | Use the fresh mode when users changed recently, and say which mode produced the evidence. | Implemented in audit_iam.py | Lab owner | 1 | 2 | 2 | Low
R14 | Lab operations | One person builds, runs and reviews everything, so mistakes are not caught by a second set of eyes. | Projects 3 and 4: one operator for every step. Evidence was captured from real output so a reader can check it. | 4 | 2 | 8 | Medium | GOVERN | GV.RR Roles, Responsibilities and Authorities | AC-5 | Accept | Accepted for a personal lab. Compensate by keeping evidence, publishing the method and inviting outside review. A real program would split build and review duties. | Accepted | Lab owner | 4 | 2 | 8 | Medium
| Summary | Count by rating |  | Inherent | Target
|  | Critical |  | 1 | 0
|  | High |  | 7 | 0
|  | Medium |  | 5 | 6
|  | Low |  | 1 | 8
|  | Total risks |  | 14 | 14
Treatment count
|  | Reduce |  | 12
|  | Accept |  | 1
|  | Avoid |  | 1
|  | Transfer |  | 0

## Method
Method and scales
Likelihood scale (1 to 5)
1 | Rare | Would need an unusual combination of events in this lab
2 | Unlikely | Possible but not expected in a year
3 | Possible | Could happen in a year with ordinary mistakes
4 | Likely | Expected to happen during a year
5 | Almost certain | Happens repeatedly
Impact scale (1 to 5)
1 | Minimal | No lasting effect, easy to redo
2 | Minor | Some rework or a short delay
3 | Moderate | Lab data or a project is lost or a job fails
4 | Major | Credentials or private data exposed in the lab
5 | Severe | Full account exposure or public data exposure
Rating bands (score = likelihood x impact)
Band | Highest score in band
Low | 4
Medium | 9
High | 14
Critical | 25
Notes and assumptions
1. Scope: one personal AWS lab account used in Projects 3 and 4. No production systems, no employer data.
2. Likelihood and impact are my own judgments for a single owner lab. They are not measured values.
3. Evidence comes from the real runs of Projects 3 and 4. Anything marked planned has not been built.
4. Target score is the score I expect after the treatment is in place. It is an estimate, not a test result.
5. Owner is the lab owner for every risk because one person runs this lab.
6. Blue cells are inputs you can change. Scores, ratings and the heat map counts recalculate.
7. Transfer is not used. A personal lab has no third party to carry the risk.
8. Control mappings are my study mappings to NIST CSF 2.0 and SP 800-53 Rev. 5, not an official crosswalk.

## Heat map
Likelihood by impact heat map (counts of risks per cell)
Inherent (before treatment) | [5 empty] | Target (after planned treatment)
Impact | [5 empty] | Impact
5 | 0 | 3 | 1 | 0 | 0 | 5 | 4 | 0 | 0 | 0 | 0
4 | 0 | 1 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0
3 | 0 | 1 | 2 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0
2 | 0 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 1 | 0
1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| 1 | 2 | 3 | 4 | 5 |  | 1 | 2 | 3 | 4 | 5
| Likelihood | [5 empty] | Likelihood
Cell colours follow the fixed bands on the Method sheet: Low up to 4, Medium up to 9, High up to 14, Critical 15 and above. If you change a band limit on the Method sheet, update the fills as well.